## NUMBERS
"Firefly MDP Sprint 7"
15 Tasks
Task | Message | Time (HR) | Task Points (TP) | HR / TP | Resolution
FA-7504 | Existing DLLs are not moved to "legacy dll" folder during the install | 11 | 0 | 0 | Fixed
FA-7496 | LegAllocQty and HedgeLegAllocQty are getting rounding in xml(RFF_Fetch and Trade_Query) and 8 message | 0 | 0 | 0 | Won't Fix
FA-7471 | Update selected bug filters in SalesDealingTicketConsistencyTest and remove spread fields from comparison | 24.17 | 5 | 4.83 | Completed
FA-7466 | FIXHandlerConsistencyTest. 17.1 Batch1 case "Sell Risk Reversal Put W/ Delta" is failing on Maximoff. Passed on Vision | 42 | 0 | 0 | Fixed
FA-7461 | Maintenance task to update TicketComparisonSalesTicketingVsSalesDealingVsAPIDealingVsTiesTest for Forward Hedge for Trade as Opposite | 26.5 | 5 | 5.3 | Unresolved
FA-7457 | Identify known bugs from Vision to determine how many can be added in a sprint | 2.33 | 3 | 0.78 | Completed
FA-7432 | Not able to Quote on some requests with forward hedge. | 15.5 | 3 | 5.17 | Cannot Reproduce
FA-7403 | Possible autobuild issue when switching between versions | 1 | 0 | 0 | Won't Fix
FA-7402 | Jenkins issue on running test after auto install | 34.5 | 0 | 0 | Fixed
FA-7371 | As a kACE user I want to include selected math dlls in the Maximoff install | 18 | 3 | 6 | Unresolved
FA-7354 | Perform analysis of nightly runs for MDP | 89.83 | 0 | 0 | Fixed
FA-7280 | As a kACE user I want to update automated tests for multiple hedges | 85.5 | 5 | 17.1 | Completed
FA-6919 | Maintenance task to Update Method getImpliedVol to get correct tkt volatility in test SalesDealingTicketConsistencyTest, StreamingHedgesDealingTicketConsistencyTest | 14.5 | 5 | 2.9 | Completed
FA-5126 | Multi Strategy Cases not getting executed in some tests in SPARK/Jenkins | 38.5 | 5 | 7.7 | Unresolved
FA-4318 | Update calculate() method to dynamically wait until calculation is finished | 33.5 | 8 | 4.19 | Completed
TOTAL |  | 436.83 | 42
AVERAGE |  | 29.12 | 2.8 | 10.4
MEDIAN |  | 24.17 | 3 | 2.9
MIN |  | 0 | 0 | 0
MAX |  | 89.83 | 8 | 17.1
RANGE |  | 89.83 | 8 | 17.1
0% QUARTILE |  | 0 | 0 | 0
25% QUARTILE |  | 12.75 | 0 | 0
50% QUARTILE |  | 24.17 | 3 | 2.9
75% QUARTILE |  | 36.5 | 5 | 5.235
100% QUARTILE |  | 89.83 | 8 | 17.1
HOURS \ TASK | 0SP (6) | 3SP (3) | 5SP (5) | 8SP (1)
AVERAGE | 29.72 | 11.94 | 37.83 | 33.5
MEDIAN | 34.5 | 15.5 | 26.5 | 33.5
MIN | 0 | 2.33 | 14.5 | 33.5
MAX | 89.83 | 18 | 85.5 | 33.5
RANGE | 89.83 | 15.67 | 71 | 0
25% QUARTILE | 3.5 | 8.91 | 24.17 | 33.5
75% QUARTILE | 40.12 | 16.75 | 38.5 | 33.5
RATE \ TASK | 3SP (3) | 5SP (5) | 8SP (1)
AVERAGE | 3.98 | 7.57 | 4.19
MEDIAN | 5.17 | 5.3 | 4.19
MIN | 0.78 | 2.9 | 4.19
MAX | 6 | 17.1 | 4.19
RANGE | 5.22 | 14.2 | 0
25% QUARTILE | 2.97 | 4.83 | 4.19
75% QUARTILE | 5.58 | 7.7 | 4.19