## NUMBERS
"Nexus Sprint 19"
8 Tasks
Task | Message | Time (HR) | Task Points (TP) | HR / TP | Resolution
FA-7306 | As a developer, I want the PA tool to subscribe and process Kafka consumer group rebalancing call backs. | 16 | 2 | 8 | Fixed
FA-7305 | As a developer, I want to statically and/or dynamically link to librdkafka library | 16 | 2 | 8 | Fixed
FA-7302 | As a developer, I want to setup CMake projects for the library and testing executable tool | 12 | 1 | 12 | Fixed
FA-7289 | Switch Deal Manager url for FENICS Direct to old.fenicsdirect.com | 3 | 0 | 0 | Completed
FA-7246 | As product owner, I would like to stop saving mass quotes | 34 | 3 | 11.33 | Unresolved
FA-7223 | As a dev, I would like to address the issue: User Enumeration Through Response Discrepancy | 9 | 1 | 9 | Unresolved
FA-7214 | As a dev, I want to use latest npm / node js along side with the existing npm / nodejs for AB2B in monaco branch | 15 | 2 | 7.5 | Unresolved
FA-6874 | As a user, I want Gateway to be performant Part 1/3: Framework for asynchronized persistence to db | 23 | 5 | 4.6 | Unresolved
TOTAL |  | 128 | 16
AVERAGE |  | 16 | 2 | 8
MEDIAN |  | 16 | 2 | 8
MIN |  | 3 | 0 | 0
MAX |  | 34 | 5 | 12
RANGE |  | 31 | 5 | 12
0% QUARTILE |  | 3 | 0 | 0
25% QUARTILE |  | 11.25 | 1 | 6.775
50% QUARTILE |  | 15.5 | 2 | 8
75% QUARTILE |  | 17.75 | 2.25 | 9.5825
100% QUARTILE |  | 34 | 5 | 12
HOURS \ TASK | 0SP (1) | 1SP (2) | 2SP (3) | 3SP (1) | 5SP (1)
AVERAGE | 3 | 10.5 | 15.67 | 34 | 23
MEDIAN | 3 | 12 | 16 | 34 | 23
MIN | 3 | 9 | 15 | 34 | 23
MAX | 3 | 12 | 16 | 34 | 23
RANGE | 0 | 3 | 1 | 0 | 0
25% QUARTILE | 3 | 9.75 | 15.5 | 34 | 23
75% QUARTILE | 3 | 11.25 | 16 | 34 | 23
RATE \ TASK | 1SP (2) | 2SP (3) | 3SP (1) | 5SP (1)
AVERAGE | 10.5 | 7.83 | 11.33 | 4.6
MEDIAN | 12 | 8 | 11.33 | 4.6
MIN | 9 | 7.5 | 11.33 | 4.6
MAX | 12 | 8 | 11.33 | 4.6
RANGE | 3 | 0.5 | 0 | 0
25% QUARTILE | 9.75 | 7.75 | 11.33 | 4.6
75% QUARTILE | 11.25 | 8 | 11.33 | 4.6