## NUMBERS
"Nexus Sprint 22"
4 Tasks
Task | Message | Time (HR) | Task Points (TP) | HR / TP | Resolution
FA-7581 | As prod owner, I would like LSV Installed on prod machine | 56 | 5 | 11.2 | Resolved
FA-7500 | As a dev, I want to learn about the Jira API and how to access the Agile Boards, The jira issue and subtasks, The SP field and the tempo logged times | 45 | 3 | 15 | Resolved
FA-7310 | As a developer, I want the member node to pick the right partitions based on current state. | 21 | 2 | 10.5 | Resolved
FA-7309 | As a developer, I want the coordinator node to recompute the PA state according to rebalance event. | 13.5 | 2 | 6.75 | Resolved
TOTAL |  | 135.5 | 12
AVERAGE |  | 33.88 | 3 | 11.29
MEDIAN |  | 45 | 3 | 11.2
MIN |  | 13.5 | 2 | 6.75
MAX |  | 56 | 5 | 15
RANGE |  | 42.5 | 3 | 8.25
0% QUARTILE |  | 13.5 | 2 | 6.75
25% QUARTILE |  | 19.125 | 2 | 9.5625
50% QUARTILE |  | 33 | 2.5 | 10.85
75% QUARTILE |  | 47.75 | 3.5 | 12.15
100% QUARTILE |  | 56 | 5 | 15
HOURS \ TASK | 2SP (2) | 3SP (1) | 5SP (1)
AVERAGE | 17.25 | 45 | 56
MEDIAN | 21 | 45 | 56
MIN | 13.5 | 45 | 56
MAX | 21 | 45 | 56
RANGE | 7.5 | 0 | 0
0% QUARTILE | 13.5 | 45 | 56
25% QUARTILE | 15.38 | 45 | 56
50% QUARTILE | 17.25 | 45 | 56
75% QUARTILE | 19.12 | 45 | 56
100% QUARTILE | 21 | 45 | 56
RATE \ TASK | 2SP (2) | 3SP (1) | 5SP (1)
AVERAGE | 8.62 | 15 | 11.2
MEDIAN | 10.5 | 15 | 11.2
MIN | 6.75 | 15 | 11.2
MAX | 10.5 | 15 | 11.2
RANGE | 3.75 | 0 | 0
0% QUARTILE | 6.75 | 15 | 11.2
25% QUARTILE | 7.69 | 15 | 11.2
50% QUARTILE | 8.62 | 15 | 11.2
75% QUARTILE | 9.56 | 15 | 11.2
100% QUARTILE | 10.5 | 15 | 11.2